Project Methodology

Waterfall Model

Time Estimation

|  | Planning | Analysis | Design | Implementation |
| --- | --- | --- | --- | --- |
| Standard percentages | 15% | 20% | 35% | 30% |
| Estimated time based on planning time | 1.5months | 2months | 3.5months | 3months |

Tasks Identification

| System Request | Name of Task |
| --- | --- |
| 1/11/2026 | Start Date |
| 7/11/2026 | End Date |
| Haidy Emad | Person assigned to task |
| High | Priority |
| Microsoft word | Resources Needed |
| 1 Week | Estimated Time |
| 4 days | Actual Time |

| Feasibility Study | Name of Task |
| --- | --- |
| 8/11/2026 | Start Date |
| 21/11/2026 | End Date |
| Rehab Ayman | Person assigned to task |
| High | Priority |
| Microsoft word | Resources Needed |
| 2 Weeks | Estimated Time |
| 10 days | Actual Time |

| Pert Chart, Gant Chart | Name of Task |
| --- | --- |
| 22/11/2026 | Start Date |
| 5/12/2026 | End Date |
| Shahd Elshiekh | Person assigned to task |
| High | Priority |
| Ms project | Resources Needed |
| 2 Weeks | Estimated Time |
| 10days | Actual Time |

| Interview | Name of Task |
| --- | --- |
| 6/12/2026 | Start Date |
| 12/12/2026 | End Date |
| Rehab Ayman | Person assigned to task |
| Medium | Priority |
| Microsoft word | Resources Needed |
| 1week | Estimated Time |
| 5days | Actual Time |

| Questionnaire | Name of Task |
| --- | --- |
| 13/12/2026 | Start Date |
| 19/12/2026 | End Date |
| Haidy Emad | Person assigned to task |
| medium | Priority |
| Form drive | Resources Needed |
| 1week | Estimated Time |
| 4days | Actual Time |

| Data Flow Diagram | Name of Task |
| --- | --- |
| 20/12/2026 | Start Date |
| 9/1/2027 | End Date |
| Shahd Elshiekh | Person assigned to task |
| High | Priority |
| Internet | Resources Needed |
| 3weeks | Estimated Time |
| 14days | Actual Time |

| Data Store | Name of Task |
| --- | --- |
| 9/1/2027 | Start Date |
| 16/1/2027 | End Date |
| Rehab Ayman | Person assigned to task |
| High | Priority |
| Microsoft word | Resources Needed |
| 1 Week | Estimated Time |
| 5 days | Actual Time |

| process specification | Name of Task |
| --- | --- |
| 17/1/2027 | Start Date |
| 1/2/2027 | End Date |
| Haidy Emad | Person assigned to task |
| High | Priority |
| Microsoft word | Resources Needed |
| 2week | Estimated Time |
| 10days | Actual Time |

| Entity Relationship | Name of Task |
| --- | --- |
| 2/2/2027 | Start Date |
| 9/2/2027 | End Date |
| Shahd Elshiekh | Person assigned to task |
| High | Priority |
| StarUML | Resources Needed |
| 1weeks | Estimated Time |
| 7days | Actual Time |

| Normalization | Name of Task |
| --- | --- |
| 10/2/2027 | Start Date |
| 24/2/2027 | End Date |
| Rehab Ayman | Person assigned to task |
| High | Priority |
| StarUML | Resources Needed |
| 2week | Estimated Time |
| 10days | Actual Time |

| design | Name of Task |
| --- | --- |
| 25/2/2027 | Start Date |
| 25/5/2027 | End Date |
| Haidy Emad | Person assigned to task |
| High | Priority |
| Visual studio code | Resources Needed |
| 3months | Estimated Time |
| 2.5 month | Actual Time |

| Implementation | Name of Task |
| --- | --- |
| 26/5/2027 | Start Date |
| 29/7/2027 | End Date |
| Shahd Elshiekh | Person assigned to task |
| High | Priority |
| Visual studio code | Resources Needed |
| 2month | Estimated Time |
| 2month | Actual Time |

|  |  |  | Estimated |  |  | Actual |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task ID | Task Name | Assigned to | Duration (Days) | Start Date | Finish Date | Start Date | Finish Date | Duration |  | Dependency | Status |  |
| A | System Request | Haidy Emad | 7 | 2026-11-01 | 2026-11-07 | 2026-11-01 | 2026-11-04 | 4 |  | - |  | Closed |  |
| B | Feasibility Study | Rehab Ayman | 14 | 2026-11-08 | 2026-11-21 | 2026-11-08 | 2026-11-17 | 10 |  | A |  | Closed |  |
| C | Pert Chart, Gantt Chart | Shahd Elshiekh | 14 | 2026-11-22 | 2026-12-05 | 2026-11-22 | 2026-11-29 | 8 |  | B |  | Closed |  |
| D | Interview | Rehab Ayman | 10 | 2026-12-06 | 2026-12-12 | 2026-12-06 | 2026-12-10 | 5 |  | C |  | Closed |  |
| E | Questionnaire | Haidy Emad | 7 | 2026-12-13 | 2026-12-19 | 2026-12-13 | 2026-12-16 | 4 |  | D |  | Closed |  |
| F | Data Flow Diagram | Shahd Elshiekh | 21 | 2026-12-20 | 2027-01-09 | 2026-12-20 | 2026-12-1 | 14 |  | E |  | Closed |  |
| G | Data Store | Rehab Ayman | 7 | 2027-01-09 | 2027-01-16 | 2027-01-09 | 2027-01-14 | 5 |  | F |  | Closed |  |
| H | Process Specification | Haidy Emad | 14 | 2027-01-17 | 2027-02-1 | 2027-01-17 | 2027-01-27 | 10 |  | G |  | Closed |  |
| I | Entity Relationship | Shahd Elshiekh | 7 | 2027-02-2 | 2027-02-09 | 2027-02-2 | 2027-02-09 | 7 |  | H |  | Closed |  |
| J | Normalization | Rehab Ayman | 14 | 2027-02-10 | 2027-02-24 | 2027-02-10 | 2027-02-20 | 10 |  | I |  | Closed |  |
| K | Design | Haidy Emad | 90 | 2027-02-25 | 2027-05-25 | 2027-02-25 | 2027-05-10 | 65 |  | J |  | Closed |  |
| L | Implementation | Shahd Elshiekh | 60 | 2027-05-26 | 2027-07-29 | 2027-05-26 | 2027-07-29 | 60 |  | K |  | Closed |  |

| Pert Chart |  |  |  |
| --- | --- | --- | --- |
| Activity | Description | Predecessors | Duration in days |
| A | System Request | - | 4 |
| B | Feasibility Study | A | 10 |
| C | Pert Chart, Gantt Chart | B | 8 |
| D | Interview | C | 5 |
| E | Questionnaire | D | 4 |
| F | Data Flow Diagram | E | 14 |
| G | Data Store | F | 5 |
| H | Process Specification | G | 10 |
| I | Entity Relationship | H | 7 |
| J | Normalization | I | 10 |
| K | Design | J | 65 |
| L | Implementation | K | 60 |